LENS PROJECT

Launch Plan

Version 2.1 — April 2, 2026

CONFIDENTIAL

PHASE 1

Validate (Now — April 2026)

Confirm that the lens document is a better representation of professional identity than a resume, and that the bidirectional scoring system produces actionable signal. Collect structured feedback from 10-15 testers.

Deliverables

- AI-guided intake form operational (LensIntake.jsx, ~2200 lines, live Claude API discovery) — DONE

- Role Lens Scorer deployed on Vercel with Gate Tolerance + Analysis Depth sliders (9 modes) — DONE

- Candidate Lens Scorer operational (lens-scorer.jsx) — DONE

- Bidirectional Lens System specification complete (role lens schema, matching algorithm, match report, feedback loop) — DONE

- User testing feedback form with Airtable backend — DONE

- Feedback Archive table for qualitative tester discussions (3 entries logged) — DONE

- Core narrative v1.0 built (single-source positioning document) — DONE

- Tester walkthrough deck (10 slides, Swiss Style) — DONE

- Session persistence with conversation history preserved across refresh — DONE

- Discovery coach guardrails (single-question constraint, config/guardrails.yaml) — DONE

- Provisional patent filed — App #64/015,187, micro entity, 3/24/26 — DONE

- Prior art search completed — no competitor filings on identity-signal matching — DONE

- IP Summary filed, Mutual NDA template ready — DONE

- James Pratt coaching persona encoded (SKILL.md) and in testing

- NDAs signed with James Pratt, Todd Gerspach, Edie McCarthy

- Edie Hunt call (April 7) — validate Hiring Leaders thesis with actual employer perspective

- Core narrative v1.1 incorporating pressure test revisions + Edie feedback

- Feature branch (session persistence + UI fixes) merged to production

- Nathan Fierley testing coaching persona implementation

| Metric | Target |
| --- | --- |
| Testers completing full discovery | 10-15 people |
| 'Feels like you' score (1-10) | Average 7+ |
| 'Better than resume' response | >70% Yes or Partially |
| 'Would share with recruiter' | >50% Yes or With Edits |
| Bidirectional score accuracy | Manual review confirms signal quality on 5+ matches |
| NDAs signed | 3/3 (James, Todd, Edie McCarthy) |

PHASE 2

Free Tool Launch (May — July 2026)

Deploy the free lens generation tool publicly. Build an email waitlist for the paid product. Establish the coach referral pipeline. Begin collecting usage data for the feedback loop.

Deliverables

- Intake form deployed publicly (Vercel, product domain TBD — tide-pool.org reserved for Archive only)

- Role Lens Scorer available as a demo for enterprise conversations (speculative — pending Edie Hunt validation)

- Email capture for paid product waitlist (Airtable or dedicated ESP)

- Todd Gerspach’s network activated for coach referrals

- James Pratt persona live as the first coach channel

- Content marketing: 2-3 LinkedIn posts per week demonstrating lens concepts

- Usage analytics tracking (which sections take longest, where users drop off)

- Feedback loop v1: explicit signals collected (pursued/skipped) on manual basis

- Lens for Beginners and Lens for Hiring Leaders updated from core narrative v1.1

| Metric | Target |
| --- | --- |
| Lens documents generated | 100+ |
| Completion rate | >60% of users who start |
| Email waitlist signups | 200+ |
| Coach partner inquiries | 3-5 coaches expressing interest |
| Average session time | 25-45 minutes (design target) |

PHASE 3

Paid Product (August — October 2026)

Connect the lens document to the n8n scoring pipeline. Launch daily briefing emails as a paid subscription ($50/month). Passive monitoring as the retention engine.

Deliverables

- Generalized scoring pipeline accepting any lens document (fork of personal v9 or new build — decision pending)

- Daily briefing email delivery (job alerts + VC portfolio matches + predictive signals)

- Stripe subscription integration ($50/month)

- Passive monitoring: lens governs continuous background scanning

- Feedback loop v2: automated signal collection (pursued/skipped/interviewed/outcome)

- Per-user weight calibration running (learning rate 0.02)

- Lens drift detection active (surfaces when actions diverge from stated preferences)

- 2-3 additional coach personas onboarded

- Enterprise pilot conversations initiated (bidirectional matching demo — contingent on Phase 1 validation of Hiring Leaders thesis)

| Metric | Target |
| --- | --- |
| Paying subscribers | 50+ by end of month 3 |
| MRR | $2,500+ |
| Briefing open rate | >50% |
| Churn rate | <10% monthly |
| Feedback signal collection rate | >30% of delivered matches get explicit feedback |
| Coach-facilitated lens quality delta | Measurable improvement vs. self-serve (A/B) |

PHASE 4

Scale (November 2026+)

Onboard coaches 5-10, launch enterprise role lens product (if validated), establish B2B2C revenue, raise seed round on the strength of the data flywheel and coach network moat.

Deliverables

- Enterprise Role Lens product: companies create role lenses, candidates scored bidirectionally (contingent on Phase 1/2 validation)

- Match Report delivery to both candidates and hiring managers

- Coach onboarding pipeline systematized (recruitment, persona encoding, testing, deployment)

- 5-10 active coach personas with revenue share agreements

- Global model improvement running (anonymized cross-user pattern learning)

- Seed raise ($750K) on demonstrated traction: subscriber count, coach network, data flywheel metrics

- Full-time engineering hire

- Convert provisional patent to nonprovisional (deadline: March 24, 2027)

| Metric | Target |
| --- | --- |
| Paying subscribers | 500+ by month 18 |
| ARR | $300K+ |
| Active coach personas | 5-10 |
| Enterprise pilots | 2-3 companies testing Role Lens (if validated) |
| Seed round | $750K raised |

KEY RISKS AND MITIGATIONS

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Discovery takes too long | High | Session persistence, progress saving, 25-45min target, section-by-section completion, single-question guardrail |
| Self-serve quality too low | High | Coach channel as quality tier, A/B measurement, continuous prompt refinement, multi-source upload enriches lens |
| Free tool indistinguishable from ChatGPT + resume | High | Structured output format (machine-readable YAML), methodology encoding (not raw chatbot), pipeline integration as the real product. Free tool is demonstration, not standalone value. |
| Enterprise thesis unvalidated | Medium | James Pratt feedback (3/30) challenges hiring-volume-over-precision assumption. Edie Hunt call (4/7) is first employer validation. Label enterprise positioning as speculative until confirmed. |
| Gaming / performative answers | Medium | Multi-source cross-referencing, coaching methodology pushes past surface, intrinsic motivation (self-directed use) is the real anti-gaming mechanism. Employer-mandated use is structurally weaker. |
| Coach adoption slow | Medium | James Pratt as proof of concept, Todd’s network for referrals, revenue share incentive |
| Competitor copies the concept | Medium | Provisional patent filed (App #64/015,187), coach network moat, data flywheel, no competitor has filed on identity-signal matching |
| API costs at scale | Low | Haiku for scoring (cheaper), Sonnet for discovery only, caching common patterns |

Eric Zelman — Lens Project — April 2, 2026